## Slide 1: HNDIT2302 IT Project Management
Project Human Resource Management

## Slide 2: Learning Objectives
Define project human resource management and describe its processes.
Summarize key concepts for managing people
Identify the tools for HR management (project organizational chart, responsibility assignment matrix, and resource histogram)
Explain the concepts of resource assignments, resource loading, and resource leveling

## Slide 3: What is Project Human Resource Management?
Project human resource management includes the processes required to make the most effective use of the people involved with a project. Processes include
  Organizational planning
  Staff acquisition
  Team development

## Slide 4: Keys to Managing People
Psychologists and management theorists have devoted much research and thought to the field of managing people at work
Important areas related to project management include
  motivation (intrinsic and extrinsic)
  influence and power
  effectiveness

## Slide 5: Motivation
Abraham Maslow developed a hierarchy of needs to illustrate his theory that people’s behaviors are guided by a sequence of needs
Maslow argued that humans possess unique qualities that enable them to make independent choices, thus giving them control of their destiny

## Slide 6: Maslow’s Hierarchy of Needs

## Slide 7: Ways to Influence that Help and Hurt Projects
Projects are more likely to succeed when project managers influence with
  expertise
  work challenge
Projects are more likely to fail when project managers rely too heavily on
  authority
  money
  penalty

## Slide 8: Power
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
Types of power include
  Coercive
  Legitimate
  Expert
  Reward
  Referent

## Slide 9: Improving Effectiveness - Covey’s 7 Habits
Project managers can apply Covey’s 7 habits to improve effectiveness on projects
  Be proactive
  Begin with the end in mind
  Put first things first
  Think win/win
  Seek first to understand, then to be understood
  Synergize
  Sharpen the saw

## Slide 10: Empathic Listening and Rapport
Good project managers are empathic listeners; they listen with the intent to understand
Before you can communicate with others, you have to have rapport
Mirroring is a technique to help establish rapport
IT professionals often need to develop empathic listening and other people skills to improve relationships with users and other stakeholders

## Slide 11: Improving Relationships Between Users and Developers
Some organizations require business people, not IT people, to take the lead in determining and justifying investments in new computer systems
CIOs push their staff to recognize that the needs of the business must drive all technology decisions
Some companies reshape their IT units to look and perform like consulting firms

## Slide 12: Organizational Planning
Organizational planning involves identifying, documenting, and assigning project roles, responsibilities, and reporting relationships
Outputs and processes include
  project organizational charts
  work definition and assignment process
  responsibility assignment matrixes
  resource histograms

## Slide 13: Organizational Planning

## Slide 14: Sample Organizational Chart for a Large IT Project

## Slide 15: Work Definition and Assignment Process

## Slide 16: Sample Responsibility Assignment Matrix (RAM)

## Slide 17: RAM Showing Stakeholder Roles

## Slide 18: Sample RACI Chart
R = responsibility, only one R per task
A = accountability
C = consultation
I = informed

## Slide 19: Sample Resource Histogram

## Slide 20: Staff Acquisition
Staffing plans and good hiring procedures are important in staff acquisition, as are incentives for recruiting and retention
Some companies give their employees one dollar for every hour a new person they helped hire works
Some organizations allow people to work from home as an incentive
Research shows that people leave their jobs because they don’t make a difference, don’t get proper recognition, aren’t learning anything new, don’t like their coworkers, and want to earn more money

## Slide 21: Staff Acquisition

## Slide 22: Resource Loading and Leveling
Resource loading refers to the amount of individual resources an existing project schedule requires during specific time periods
Resource histograms show resource loading
Overallocation means more resources than are available are assigned to perform work at a given time

## Slide 23: Resource Leveling
Resource leveling is a technique for resolving resource conflicts by delaying tasks
The main purpose of resource leveling is to create a smoother distribution of resource usage and reduce over allocation

## Slide 24: Resource Leveling Example

## Slide 25: Team Development
It takes teamwork to successfully complete most projects
Training can help people understand themselves, each other, and how to work better in teams
Team building activities include
  physical challenges
  psychological preference indicator tools

## Slide 26: Team Development

## Slide 27: Social Styles Profile
People are perceived as behaving primarily in one of four zones, based on their assertiveness and responsiveness:
  Drivers
  Expressives
  Analyticals
  Amiables
People on opposite corners (drivers and amiables, analyticals and expressives) may have difficulties getting along

## Slide 28: Social Styles

## Slide 29: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
Focus on rewarding teams for achieving specific goals
Allow time for team members to mentor and help each other to meet project goals and develop human resources

## Slide 30: General Advice on Teams
Focus on meeting project objectives and producing positive results
Fix the problem instead of blaming people
Establish regular, effective meetings
Nurture team members and encourage them to help each other
Acknowledge individual and group accomplishments

## Slide 31: Using Software to Assist in Human Resource Management
Software can help in producing RAMs and resource histograms
Project management software includes several features related to human resource management such as
  viewing resource usage information
  identifying under and overallocated resources
  leveling resources

## Slide 32: Resource Usage View from Microsoft Project

## Slide 33: Resource Usage Report from Microsoft Project

## Slide 34: Project Human Resource Management

## Slide 35: References
“Information Technology Project Management”, Kathy Schwalbe, sixth Edition, THOMSON Course Technology